## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | Estimate (hrs) | MOSCOW | Dependency | Assignee | Status
1 | 1 | US101 | RoomService API Testing (CRUD + Auth) | 0.5 | MUST HAVE |  | t1 | 3-Done
1 | 1 | US102 | Create Postman Collection for Sprint‑3 | 0.5 | MUST HAVE | US101 | t1 | 3-Done
1 | 1 | US103 | Implement Positive API Tests | 0.25 | MUST HAVE | US001 | t1 | 3-Done
1 | 1 | US104 | Implement Negative API Tests | 2 | MUST HAVE | - | t1 | 3-Done
1 | 1 | US105 | Bug: UpdateRoomPrice works without authentication | 1 | MUST HAVE | US104 | t1 | 3-Done
1 | 1 | US106 | Bug: DeleteRoomById works without authentication | 1 | MUST HAVE | - | t1 | 3-Done
1 | 1 | US107 | Bug: AddRoom works without authentication | 0.5 | SHOULD HAVE | US106 | t1 | 3-Done