## Sheet1
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 9.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US101 | T001 | As a QA, I want to perform Authentication (Login + Token) testing for RoomService API | 2025-08-04 | 2025-08-04 | Shoal Koley | Build | 3- Completed | 0.25 | Day 1: 0.25; Day 2: 0; Day 3: 0
US102 | T002 | As a QA, I want to test all RoomService APIs (View, Add, Update, Delete) using Postman | 2025-08-04 | 2025-08-04 | Harsh Shukla | Build | 3- Completed | 0.25 | Day 1: 0.25; Day 2: 0
US103 | T003 | As a QA, I want to validate positive and negative API scenarios for RoomService API | 2025-08-04 | 2025-08-04 | Harsh Shukla | Build | 3- Completed | 1.5 | Day 1: 0.25
US104 | T004 | As a QA, I want to generate test execution report for all API test cases | 2025-08-04 | 2025-08-04 | Shoal Koley | Design | 3- Completed | 6 | Day 1: 0.25
US105 | T005 | As a QA, I want to log bugs for any unauthorized API success in Jira | 2025-08-04 | 2025-08-04 | Gyanesh Tiwari | Build | 3- Completed | 0.25 | Day 1: 0.25